## Open Topics 2019
Summary of Outstanding Items - Board 12.03.2019
Item | Board | Action | Completed/
| Date |  | In Progress
Member Services
1 | 2019-01-19 | Sabine to convene special board meeting to discuss new membership model. | Y/11.02.2019
2 | 2019-01-19 | Eberhard and Elizabeth to review friends list identify potential for conversion to members. | N
3 | 2019-01-19 | All board members to recruit 2 new Corporate Members each.
|  | Andre to follow up with Group of Eight, University of Melbourne, and Innotrans delegation while in Australia. | ?
|  | Elisabeth to contact OzForex. | ?
Work in progress
4 | 2019-01-19 | David to advise on Austrade’s calendar of activities and delegations (e.g. Hannover Messe). | Work in progress
5 | 2019-01-19 | Evangelos to check on potential parliamentary event. | ?
6 | 2019-02-11 | New Fee Structure: Eberhard will look through our records from last year’s events and come up with a calculation for a possible new fee structure, incl. various models such as free events
7 | 2019-02-11 | Annual Sponsor Sabine, Peirui, Eberhard and Malte will come up with a suggestion by the end of this week.
8 | 2019-03-12 | Further Discussion of Membership Model/Change of Offering including offer to annual sponsor and to young members (Next Gen)(all BMs)
9 | 2019-03-12 | New Fee Structure: Eberhard to distribute his first thoughts to the board.
Events
1 | 2019-02-11 | Webinars: Rob to liaise with Elizabeth and sends around possible dates for three webinars
2 | 2019-02-11 | Updating Event Calendar ACTION: Peirui | done
3 | 2019-02-11 | Quality Management Events ACTION: Peirui developed list of Key Tasks for Event Manager, Admin and Board Members; Peirui and Malte to act as QA managers. ACTION: List to be sent to board members after events meeting | done
Communication
1 | 2019-01-19 | Kiki to circulate approved marketing plan with following actions: | Work in progress
- Kiki to refine survey and to send it out through office email with link to survey by 31 Jan 2019.
- Kiki and Sergej to review website for optimization by Feb 2019.
- Kiki to develop content plan and social platform tone/guidelines by Feb 2019.
- Kiki to review options for YouTube productions.
2 | 2019-03-12 | Survey: Kiki to distribute the result of the survey.
Engagement
1 | 2019-01-19 | David and Kiki to look into plan for engaging next generation (2H2019). | Work in progress
2 | 2019-02-11 | Policy: Submission regarding FTA
ACTION: Elizabeth to develop first draft
ACTION: Rob to support Elizabeth and Sabine with submission
ACTION: Sabine to talk to international group regarding the possibility of a joint submission (to be decided)
Admin
1 | 2019-01-19 | Sabine to send 2019 board dates. Agenda to include new conference dial-in details, 10 -15 minutes for tracking of strategy/KPIs every 2 – 3 months and rolling list of actions arising. | done
2 | 2019-01-19 | Eberhard and David to review document management. | Work in progress
3 | 2019-01-19 | Elisabeth and Sergej to distribute review of 2018 Operational Plan and finalised 2019 Operational Plan. | 2018 distributed, 2019 coming up
4 | 2019-01-19 | Eberhard to complete financial audit with Werner prior to AGM. | done
5 | 2019-01-19 | Peirui to circulate Event Request Form. | done
6 | 2019-01-19 | Elizabeth and Cherokee to send around working days/hours. | done
7 | 2019-01-19 | Eberhard and Sergej working on IT/GDPR updates. Eberhard to advise IT vendor to respond to Elizabeth on website matters. | Work in progress
8 | 2019-01-19 | Elisabeth to write-up dinner notes on Ambassador’s briefing for posting on website. | N
9 | 2019-01-19 | Sabine and Eberhard to confirm AGM Date (week of 18 March 2019) and potential to tie-in with an event by 25 Jan 2019. | Date set: 19.03.
10 | 2019-01-19 | Sergej and Elizabeth to upload profiles of Kiki and David on website. | Work in progress
11 | 2019-01-19 | Elizabeth to circulate to board members: high-resolution version of our logos. | done
12 | 2019-02-11 | Update IT/GDPR All-we-Are will not extend the website support. New support provider needed. ACTION: Eberhard and Sergej to look into the issue
13 | 2019-02-11 | David to provide conference call solution through Austrade for next board update.
14 | 2019-03-12 | AGM – Preparation slides ongoing, reminder needs to be send, Action: Office | done
15 | 2019-03-12 | Update GDPR/IT/New website support
16 | 2019-03-12 | Action: GDPR – AllweAre to provide final statement à Eberhard
17 | 2019-03-12 | Action: Website support – develop RfP – URGENT à Sergej/Kiki
18 | 2019-03-12 | Action: Revision website = Prio 2 à Sergej/Kiki